## Development Steps
Cod Activitate | Activitate | Durata (zile) | Probleme ridicate |  | Raspuns
A | Lista componente initiale | 1 | Putem folosi arduino nano/uno sau vor fi probleme de stabilitate? |  | uno , mega, node(esp3286) -
B | Realizare conexiune Arduino - Master DMX | 2 | Putem determina capatul de cursa din torque ul motorului? |  | NUJ
C | Citire pachete Master DMX - Arduino | 2 | Exista driver stepper cu masurare curent tras? |  | DA
D | Decodare pachete Arduino | 1 | Sunt necesare end-stopperele? |  | NUJ
E | Implementare clasa "Motor" cu atribute aferente | 1 | How about splitter de retea in loc de placa de retea dual port? |  | NU: portocolul DHCP nu va lasa
F | Implementare parametrii statici clasa "Motor" | 1 | Nu gasesc interfata ether duala.. poate folosim direct mufe cu fire lipite direct pe pinii controller-ului |  | Solved
G | Atribuire valori pachet - atribute "Motor" | 1
H | Testare ansamblu cu tot cu motor montat | 1
I | Implementare afisaj digital cu potentiometru setare canal | 2
J | Testare ansamblu diverse canale | 1
K | Implementare comunicare master - slave Arduino - Arduino | 3
L | Testare comunicare Arduino - Arduino | 1
M | Testare ansamble finale | 2
N | Implementare PCB custom pe baza prototipurilor | ?
|  |  | Total Zile: | 17

## Componente
Piesa | Link | Pret | Alternative
Stepper driver | https://ardushop.ro/ro/printare-3d/1250-tmc2130-v12.html?gclid=CjwKCAjw87SHBhBiEiwAukSeUboJRXGsMfX1CMXFBGNgx4vpVBOD2Y9pCASWIF4SpyCruQEKLjjEthoCqdsQAvD_BwE | 53 | https://cleste.ro/driver-motor-pas-cu-pas-lv8729.html?utm_medium=GoogleAds&utm_campaign=ShoppingAds&utm_source=&gclid=CjwKCAjw87SHBhBiEiwAukSeUXIqnyCP5fJPpyaaMpAyx6KMzGyDXraoCz1Z3KZvrtIC4tdBb4rlqRoCTyQQAvD_BwE
https://ro.farnell.com/trinamic/tmc2300-la-t/motor-driver-40-to-125deg-c/dp/3255564?gclid=CjwKCAjw87SHBhBiEiwAukSeUQi6zqOQlL6hR6sUXhU3Otw3HrhUNki4IhD7sag_5Bq5MN6O20i3kRoCAo8QAvD_BwE&mckv=hVjDfQy4_dc¦pcrid¦526130261475¦&CMP=KNC-GRO-GEN-SHOPPING-Whoop-7-June-2021&gross_price=true
LCD Display | https://ro.farnell.com/dfrobot/dfr0287/gravity-lcd-shield-arduino-board/dp/3517914?gclid=CjwKCAjw87SHBhBiEiwAukSeUfrGk3AyIPXmZ3EsNcBBUQ1NT9ycyEkRrb8FrWcQEbBoycc69337nBoC9AEQAvD_BwE&mckv=hyjzI4Ya_dc¦pcrid¦526130261463¦&CMP=KNC-GRO-GEN-SHOPPING-Whoop-7-June-2021&gross_price=true | 87
https://cleste.ro/modul-lcd-1602-albastru-cu-butoane.html?utm_medium=GoogleAds&utm_campaign=ShoppingAds&utm_source=&gclid=CjwKCAjw87SHBhBiEiwAukSeUeh_MT5StL1LPntG_xEB8vHpiJ0rBssUgvtXb0R85T8UJf0JFgbbqBoC6TgQAvD_BwE